East Grant Region Economic Planning Project

Steering Committee Meeting

10-10-19

Attending:	Elbridge, Judy, Dwayne, Jackie, Denise, Wayne, Peggy, Sarah

| Topic | Discussion Highlights | Next Steps/Update | Lead/Timing |
| --- | --- | --- | --- |
| - Affirm project goals | Project goals affirmed by group. New goal identified and added on communication. ## Improve the quality of life for the people who live, work and visit the twelve communities in the region. ## Capitalize on regional momentum and investments that have been made over the past five years. ## Prepare a regional economic feasibility study to guide short and long term priorities and investments. - Maintain consistent communication with the community at large to keep residents informed and engaged. ## Develop a collective “voice” for the region to influence state and regional initiatives that can impact quality of life and economic stability. | None |  |
| - Affirm sub-region boundaries | Discussion about including more of Baskahegan Lake area. | Elbridge to revise map to include this area and recommend southern boundary. | Completed and attached. |
| - Affirm project deliverables | Project deliverables below affirmed by group. - Prepare a written regional economic feasibility study that: - Utilizes, where appropriate, product and progress from 2019 regional planning efforts prior to execution of contract. - Completes comprehensive asset mapping with all key stakeholders and communities in the region; - Identifies the major goals and strategies for economic development in the region; - Identifies priority projects and required investment. - Identify how to build and maintain the organizational capacity to sustain the initiatives. - Identify funding strategies for both short and long-term projects. - Prepare the final study document for dissemination and presentation to key stakeholders. | None |  |
| - Update on funding | - TIFF funds received. Will be sent to SCEC. $10,000 - Private donations received. Will be sent to SCEC. $8500 - MCF Downeast Innovation Grant wll be submitted by 10-15-19 for $10,000. - Contract for services with Sarah will be through SCEC. | Sarah to send draft contract to Charles at SCEC. | Immediate |
| - Review project design | - Sarah reviewed the attached project design with the group. Consultant and committee responsibilities discussed. Committee members in agreement but noted that work/family schedules may limit full participation for some people. - The importance of representation by more communities was discussed. The goal will be to have 1 person from each of the communities in the region involved. A list of possible people was brainstormed. | List of possible representatives attached. Elbridge and other members to reach out as asked. | Immediate TO DATE: Kyle Burdick and Heather Zapokosky have agreed to join the committee Asking David Apgar and Sue Szwed |
| - Challenges/Opportunities | - Dwayne and Peggy presented an update on the high school consolidation initiative - Elbridge and others updated on the Forest City Dam. | Keep close watch on both initiatives as they have a major impact on economic planning. | Ongoing |
| - New Items | - Identified the for: - A list of talking points about this project that all committee members can use at community meetings - A press release about the project - An article about the negative economic impact on the region with a school consolidation. - Sarah asked Judy to review all the Visitors and Tourism magazines and websites to see how the region is represented, or not. | - Sarah to develop a draft list of talking points - Elbridge to draft press release and article on school consolidation for review by group. - Judy to review tourism information and report back when ready. | By next meeting |
| - Next Steps | - Sarah to meet with Tora Johnson UMM on asset mapping with GIS system. - Sarah to talk/meet with Madison (student) to see if she is interested in working on this project. - Sarah to continue to consolidate asset mapping information completed to date. - Sarah/Elbridge to finalize community list to schedule asset mapping meetings | - Sarah met with Torah on 10/18. Intern identified to begin working in November. Details to be finalized. | Focus of next committee meeting. |

EGREPP Steering Committee – Blue indicates current committee members as of 10-28-19

Dave Conley – town?  dave@canoethewild.com

Joe Dahl – town?  josephdahl@aol.com

| Community | Name | Email | Phone | Primary Affiliation |
| --- | --- | --- | --- | --- |
| Amity | ??? |  |  |  |
| Bancroft Twp | Mitch Lansky? Sandy? Jones? | lanskymitch@gmail.com |  | Organic farmer, writer |
| Brookton Twp | Jill/Buck Plummer? |  | 448-2260 (w) |  |
| Brookton Twp | Kyle Burdick | kyle@baskahegan.com |  | Baskahegan Company |
| Codyville Plt (N) | ??? |  |  |  |
| Danforth | Ardis Brown | townofdanforth@gmail.com | 448-2321 (w) | Danforth Town manager |
| Danforth | Jackie Morse | jmorse@machiassavings.com | 448-9048 (w) | Machias Savings Bank manager |
| Danforth | David Apgar | dapgar@eastgrandschool.org |  | EGS teacher, Farm owner, Guide |
| Drew Plt East | Jimmy Potter? Smallees? |  |  |  |
| Forest City | Phil McLulleon? |  |  |  |
| Forest Twp | ??? |  |  |  |
| Haynesville | ??? |  |  |  |
| Orient | Heather Zapokosky |  |  | Small Business owner |
| Reed Plt | Sue Szwed | sdszwed@gmail.com |  |  |
| Topsfield (N) | ??? |  |  |  |
| Weston | Elbridge/Judy Cleaves | egcleaves@pwless.net | 557-9474 (h) | CORE, Guide |
| Weston | Dwayne Young | townofweston@pioneerwireless.net | 448-2316 (w) | Weston Town manager |
| Weston | Denise/Wayne Smith | denise.wayne.smith@gmail.com |  | First Settlers Lodge owner |
| Winn | Peggy White | mwhite@eastgrandschool.org | 448-2260 (w) | East Grand School superintendent |
| T8R4 NBPP | ??? |  |  |  |
| T8R3 NBPP | ??? |  |  |  |
| T7R2 NBPP (N) | ??? |  |  |  |
| T11R3 NBPP | ??? |  |  |  |